INSTITUTE OF COMPUTER

ENGINEERING TECHNOLOGY

Diploma in Software Engineering

PROJECT PROPOSAL

Project Little Wonders

Group Name 	: Team 4

Batch   		: iCD122/iCD125

Group Supervisor  :

# About the Group

| No | Student Name | Student ID | Batch | Role |
| --- | --- | --- | --- | --- |
| 01 | Jinani Sandamali | PR26122167 | 122/iCD | Member |
| 02 | Kaveesha Nethmini | PR26122178 | 122/iCD | Member |
| 03 | Prasanna Perera | PR26122118 | 122/iCD | Member |
| 04 | Shasindu Pramod | PR26122148 | 122/iCD | Member |
| 05 | Sathsidu Rupasinghe | PR26122210 | 122/iCD | Member |
| 06 | Vinush Ravithra | PR26122202 | 122/iCD | Member |
| 07 | Charuka Nuwantha | PR26122156 | 122/iCD | Member |
| 08 | Roneth Methnada | PR26122213 | 122/iCD | Member |
| 09 | Minindu Prabhaswara | PR26122194 | 122/iCD | Member |
| 10 | Janindu Akash | PR26122186 | 122/iCD | Member |
| 11 | Venuja Jayasuriya | PR26125090 | 125/iCD | Member |

[For your supervisor use only]

### Project Approval [APPROVED / REJECTED]

The proposed project aligns with the Institute’s Code of Conduct and is considered feasible for completion by the designated project party. Accordingly, approval is hereby granted for the project to proceed with implementation under the supervision and coordination of the relevant supervisors and administrators.

| Designation | Supervisor Name | Approval | Signatory | Date |
| --- | --- | --- | --- | --- |
| Group Supervisor |  |  |  |  |
| Academic Coordinator |  |  |  |  |
| Head of Academic Department |  |  |  |  |

Note (if any) :

# Table of Contents

Should use table of content generator for this.

Contents

About the Group	2

Table of Contents	4

List of Figures	5

List of Tables	5

Executive Summery	6

1. Introduction & Background	7

1.1 About the Purpose	7

1.2 Project Overview	7

2. Problem Statement	9

2.1 Problem Statement	9

2.2 Supporting Evidence	9

3. Goal & Objectives	10

3.1 Overall Goal	10

3.2 Objectives	10

4. Target Beneficiaries & Stakeholder Analysis	11

4.1 Beneficiaries	11

4.2 Stakeholder Map	12

5. Project Description	13

5.1 Key Activities	14

6. Expected Outcomes and Output	15

6.1 Expected Outcome	15

6.2 Outcome & Impact	15

7. Timeline & Implementation Plan	16

7.1 Project Timeline	16

8. Budget	17

9. Ethics, Safeguarding and Data Protection	18

10. Conclusion	18

11. Appendices	19

# List of Figures

# List of Tables

Table 1: About beneficiaries .......................................................................................................... 11

Table 2: Stakeholder map .............................................................................................................  12

Table 3: Activity table ................................................................................................................... 14

Table 4: Outcome and impact ........................................................................................................15

Table 5: Project timeline ................................................................................................................16

Table 6: Budget distribution ......................................................................................................... 17

Table 7: Gantt Chart ...................................................................................................................... 19

# Executive Summery

Project Little Wonders is a student-led Corporate Social Responsibility (CSR) initiative designed to provide approximately 15 preschool children with a safe, enjoyable, and enriching experience outside their normal classroom routine. The project responds to the need for additional opportunities for young children to participate in creative, social, recreational, and educational activities while complementing the work of preschool teachers.

The project will be implemented over three weeks of preparation and one two-to-three-hour program session at a selected preschool. Before implementation, the team will consult the preschool administration and teachers to confirm the children's needs, available facilities, suitable activities, and any additional learning resources that would be useful. The program will include at least three structured group sessions using age-appropriate activities such as storytelling, drawing, music, creative tasks, and interactive games.

Approximately 15 participating children will receive an age-appropriate educational gift pack. Where appropriate and subject to identified need, additional learning resources will also be provided to the preschool. The project will be delivered by the ten student team members under the guidance of the institute and preschool staff.

The estimated direct project cost is   LKR 27,250,   with a 10% contingency of   LKR 2,725, giving a total project budget of   LKR 29,975,   rounded to a funding ceiling of   LKR 30,000. The expected impact is improved opportunities for children's participation, creativity, communication, cooperation, and enjoyable learning, while student volunteers develop teamwork, leadership, planning, communication, and social responsibility skills.

# Introduction & Background

Early childhood is an important stage of development during which children establish cognitive, social, emotional, and communication skills. Experiences during these early years can influence how children interact with others, explore their surroundings, and approach learning.

As part of our Corporate Social Responsibility (CSR) initiative, our student team has introduced “  Project  Little Wonders  ”  ,  a community-focused project designed to create a meaningful and enjoyable experience for preschool children. The initiative brings student volunteers and young children together through a planned program that combines interaction, recreation, creative activities, and educational support.

## About the Purpose

The primary purpose of Project Little Wonders is to provide preschool children with an opportunity to step away from their usual routine and experience a positive and enjoyable day in a supportive environment.

The project also aims to encourage meaningful interaction between children and student volunteers while creating opportunities for participation, confidence, cooperation, creativity, and selfexpression. Through this initiative, the student team intends to contribute its time, skills, and resources to the preschool community.

## Project Overview

Project Little Wonders is a student-led CSR initiative that will be conducted at a selected preschool with approximately 15 participating children. The program will take approximately two to three hours and will be finalized in consultation with the preschool teachers or administration.

The program will include three main age-appropriate group games planned by the project team, along with additional interactive games where time and circumstances permit. The activities will be selected and conducted according to the children's age, interests, abilities, safety requirements, available facilities, and the preschool's requirements. This approach will allow the project team to maintain flexibility while ensuring that the program remains enjoyable, engaging, and suitable for the participating children.

Student volunteers will facilitate and support the activities while maintaining a safe, friendly, and inclusive environment where all participating children can engage comfortably. Following the activities, refreshments will be provided, and each participating child will receive an educational gift pack containing age-appropriate learning materials or useful items. Additional learning resources may also be provided to the preschool if a specific educational need is identified during the preliminary consultation.

# Problem Statement

## Problem Statement

Early childhood development relies heavily on opportunities for play, communication, and creative exploration. However, access to enrichment opportunities and supplementary learning resources varies significantly across Sri Lankan preschools, often limiting children's exposure to interactive non-classroom activities.

"Project Little Wonders" addresses this gap by offering a structured enrichment session and tailored educational support. Rather than applying a one-size-fits-all approach, the project utilizes a preliminary needs assessment to deliver support aligned with the host preschool's specific needs.

## Supporting Evidence

Early childhood development frameworks recognize that children's development is supported by nurturing relationships, safe environments, responsive interaction, and opportunities for early learning. The World Health Organization emphasizes responsive caregiving and early learning as important components of healthy early childhood development (World Health Organization, 2020). UNICEF also highlights the importance of children's early experiences and interactions, including opportunities for play, communication, and responsive support, in promoting learning and development during the early years (UNICEF, 2020).

These principles provide a relevant foundation for Project Little Wonders. However, the project will not assume that all preschool settings have identical needs. A preliminary consultation will therefore be conducted with the selected preschool before implementation. The consultation will focus on identifying the children's interests, existing learning materials, available facilities, and areas where additional support may be beneficial. This needs-based approach will help ensure that the project is relevant to the participating children and provides practical support according to the requirements of the selected preschool.

# Goal & Objectives

## Overall Goal

The overall goal of Project Little Wonders is to contribute to the positive development and wellbeing of preschool children by creating opportunities for meaningful interaction, self-expression, exploration, and enjoyable learning within a supportive environment.

The project also seeks to promote student involvement in community service by enabling volunteers to contribute their time, skills, and resources to the selected preschool.

## Objectives

The project aims to achieve the following specific objectives:

- To engage approximately 15–20 preschool children in a structured two-to-three-hour program that provides meaningful and age-appropriate recreational and educational experiences.

- To conduct at least three structured group sessions that encourage children's participation, communication, cooperation, creativity, and self-expression.

- To provide 100% of participating children with an age-appropriate educational gift pack containing selected learning or creative materials, while providing additional resources to the preschool based on its identified needs.

- To ensure that all planned activities are conducted in a safe, inclusive, and childfriendly environment, taking into consideration the age, abilities, interests, and comfort levels of the participating children.

# Target Beneficiaries & Stakeholder                       	                        Analysis

## Beneficiaries

| Beneficiary Group | Estimated Number | Selection Criteria | Expected Benefit |
| --- | --- | --- | --- |
| Direct: Preschool children | Approximately 15 | Children enrolled at the selected preschool, with preschool administration approval | Participation in creative, social, recreational, and educational activities; educational gift pack; positive group experience |
| Indirect: Preschool teachers | As applicable | Teachers/staff of the selected preschool | Additional activity support and learning resources where needs are identified |
| Indirect: Parents/families and local community | Not quantified | Connected to participating children and preschool | Positive community engagement and support for children's enrichment |
| Student volunteers | 10 | Members of Team 4 | Development of teamwork, leadership, communication, planning, and social responsibility skills |

Table 1: About beneficiaries

Geographical Coverage Geographical Coverage: A selected community preschool located in the Ingiriya Divisional Secretariat Division, Kalutara District, Western Province, Sri Lanka.

(The exact preschool will be confirmed following formal administrative approval)

## Stakeholder Map

| Stakeholder | Role / Interest | Influence | Engagement Plan |
| --- | --- | --- | --- |
| Preschool children | Primary beneficiaries; participate in activities | High | Conduct safe, inclusive, and enjoyable activities and monitor participation |
| Preschool teachers / administration | Provide guidance, permissions, and information about children's needs | High | Consult before implementation, coordinate activities, and obtain feedback |
| Project Team | Plan, fundraise, prepare, conduct, and evaluate the project | High | Regular meetings, task allocation, progress monitoring, and final reporting |
| Institute / Supervisor | Provide academic guidance, approval, and oversight | High | Submit proposal, obtain approval, provide progress updates, and seek guidance when required |
| Parents / guardians | Support children's participation and consent requirements where applicable | Medium | Communicate through the preschool and follow its consent procedures |
| Sponsors / donors / community supporters | Potential financial or inkind support | Medium | Provide a clear project budget, funding request, and accountability for contributions |

Table 2: Stakeholder map

# Project Description

Project Little Wonders is a community-based CSR project designed to give preschool children a positive and enjoyable learning experience. The project team will first select a suitable preschool and communicate with the teachers or administration. The team will identify the children's needs, suitable activities, safety considerations, and materials that may be useful.

After the planning stage, the team will prepare the required materials and activities. The program will include at least three structured sessions using simple age-appropriate activities such as storytelling, drawing, music, creative work, and group games. Student volunteers will guide the children and make sure participation is safe and inclusive.

To ensure the highest standards of safety, quality, and coordination, all activities will be facilitated under the continuous physical supervision of preschool staff and guided by strict safeguarding protocols. Student volunteers will be assigned dedicated roles—covering activity facilitation, logistics, timekeeping, and child safety—allowing the event to proceed seamlessly according to the planned timetable while maintaining a nurturing, encouraging environment for all children.

At the end of the program, refreshments and educational gift packs will be given to the participating children. Additional learning materials may also be donated to the preschool if a specific need is identified and the budget permits. Feedback will then be collected from preschool staff and the team will prepare a final project report.

## Key Activities

| No. | Activity | Description / Deliverable | Timeline | Responsible Party |
| --- | --- | --- | --- | --- |
| 1 | Select preschool and conduct needs consultation | Selected preschool; permission/coordination confirmed; children's needs and suitable activities identified | Week 1 | Project Team + Preschool Staff |
| 2 | Fundraising and procurement | Funds/in-kind support obtained; materials, refreshments, prizes, and gift-pack items purchased/prepared | Week 2 | Project Team |
| 3 | Prepare sessions and gift packs | At least three activity sessions finalized; materials and approximately 15 gift packs prepared | Week 2 | Project Team |
| 4 | Conduct CSR program | Two-to-three-hour children's program implemented safely with teacher support | Week 3 | Project Team + Preschool Staff |
| 5 | Feedback, evaluation and final report | Feedback collected; participation and outputs reviewed; final report completed | Week 3 | Project Team |

Table 3: Activity table

# Expected Outcomes and Output

## Expected Outcome

The project is expected to provide approximately 15 preschool children with a positive and meaningful experience in which they can communicate, play, create, learn, cooperate, and participate with others. The project will also give student volunteers practical opportunities to develop teamwork, leadership, communication, planning, and social responsibility skills.

## Outcome & Impact

| Level | Expected Result | Measurement Indicator | Target |
| --- | --- | --- | --- |
| Output 1 | A 2–3 hour interactive activity program is completed. | Program execution according to approved agenda | 1 Event / Program |
| Output 2 | Delivery of structured group sessions and gift packs. | Number of sessions conducted & packs distributed | Minimum 3 Sessions And 15 Gift Packs (100% of children) |
| Outcome 1 | Active participation, communication, and creative engagement among children. | Facilitator observation & recorded participation rate | ≥80% active child participation |
| Outcome 2 | Development of leadership, teamwork, and project management skills among volunteers. | Duty checklist completion & team post-event reflection | 100% participation (All 10 team members) |
| Long-term Impact | Enhanced early childhood learning exposure and ongoing utilization of donated materials. | Preschool teacher feedback & resource assessment | Positive institutional feedback & ongoing material use |

Table 4: Outcome and impact

# Timeline & Implementation Plan

The project will be implemented through three preparation and delivery phases over three weeks.

The exact event date will be confirmed with the selected preschool and the institute/supervisor.

## Project Timeline

| Phase | Key Activities | Duration | Milestone |
| --- | --- | --- | --- |
| Phase 1: Planning & Preparation | Select/contact preschool; obtain permission; conduct needs consultation; finalize initial plan and responsibilities | Week 1 | Preschool selected and plan agreed |
| Phase 2: Fundraising & Activity Preparation | Fundraising; purchase/collect materials; prepare activities, prizes, refreshments, and gift packs | Week 2 | Resources prepared for implementation |
| Phase 3: Event Implementation & Evaluation | Conduct two-to-three-hour CSR program; distribute gift packs; collect feedback; complete evaluation and final report | Week 3 | Program completed and final report prepared |

Table 5: Project timeline

# Budget

| No. | Activity / Item | Quantity | Unit Cost (Rs.) | Total (Rs.) |
| --- | --- | --- | --- | --- |
| 1 | Gift Packs |  |  |  |
| 1.1 | Toy | 15 | Included |  |
| 1.2 | Gift pack items | 15 | 750 | 11,250 |
| 1.3 | Gift-pack materials & packing | 1 | 1,000 | 1,000 |
|  | Gift Pack Total |  |  | 12,250 |
| 2 | Games |  |  |  |
| 2.1 | Chocolates / game rewards |  |  | 2,000 |
| 2.2 | Toys / prizes |  |  | 2,500 |
| 2.3 | Other game materials |  |  | 1,000 |
|  | Games Total |  |  | 5,500 |
| 3 | Treats / Refreshments |  |  |  |
| 3.1 | Snacks / Juice |  |  | 1,500 |
| 3.2 | Cake | 1 | 3,000 | 3,000 |
|  | Treat Total |  |  | 4,500 |
| 4 | Transportation |  |  | 4,000 |
|  | GRAND TOTAL (including 10%) |  |  | 29,975 |

Table 6: Budget distribution

Recommended funding ceiling: LKR 30,000 (rounded from the calculated total of LKR 29,975). Any surplus from rounding or savings should be used only for approved project needs or returned/handled according to the institute's requirements.

# Ethics, Safeguarding and Data Protection

The project team will follow the following ethical and safety practices:

- Get permission from the preschool before conducting the project.

- Keep children safe during all activities.

- Avoid activities that may cause physical or emotional harm.

- Treat all children equally without discrimination.

- Respect children's privacy.

- Do not collect unnecessary personal information.

- Take photographs or videos only with proper permission.

- Do not share children's personal information publicly without permission.

- Make sure all activities are suitable for the children's age and abilities.

- Student volunteers will follow the instructions given by preschool teachers.

# Conclusion

Project Little Wonders is a small-scale but meaningful CSR initiative that aims to create a positive and enriching experience for preschool children. Through educational activities, creative work, games, interaction, and age-appropriate resources, the project will provide children with additional opportunities to learn, communicate, cooperate, and have fun in a supportive environment.

The project will also allow the ten-member student team to contribute to the community while developing teamwork, leadership, communication, planning, and social responsibility skills. With an estimated funding ceiling of LKR 30,000 , the project seeks support from appropriate sponsors, donors, small businesses, and community members. All spending and contributions should be documented to maintain transparency and accountability.

# Appendices

- Appendix   A – Detailed Implementation Schedule

| Task | Week 01 | Week 02 | Week 03 |
| --- | --- | --- | --- |
| Project Planning |  |  |  |
| Select and Contact Preschool |  |  |  |
| Assign Team Responsibilities |  |  |  |
| Fundraising |  |  |  |
| Collect Gifts |  |  |  |
| Prepare Games& Activities |  |  |  |
| Prepare Gift Packs |  |  |  |
| Final Event Preparation |  |  |  |
| CSR event at preschool |  |  |  |
| Gift distribution |  |  |  |
| Collect Feedback |  |  |  |
| Final Report |  |  |  |

Table 7 - Gantt Chart

- Appendix   B – Supporting Research / Evidence.

The project is supported by information from the World Health Organization and UNICEF about the importance of early childhood development, learning, play, communication, and supportive relationships.

  - UNICEF. (n.d.). Care for Child Development.

United Nations Children's Fund.

https://www.unicef.org/documents/care-child-development

  - UNICEF. (n.d.). Early childhood development.

United Nations Children's Fund.

https://www.unicef.org/early-childhood-development

  - UNICEF Sri Lanka. (n.d.). Education in early childhood.

UNICEF Sri Lanka.

https://www.unicef.org/srilanka/education-early-childhood

  - World Health Organization. (2018). Nurturing care for early childhood development: A framework for helping children survive and thrive.

World Health Organization.

https://www.who.int/publications/i/item/9789241514002

  - World Health Organization.  (2020). Improving early childhood development: WHO guideline. World Health Organization.

https://www.who.int/publications/i/item/97892400020986